## Master Checklist
# | Category | Priority | Item | Description | File(s) Affected | Effort | Status
SECURITY
1 | Security | CRITICAL | Add rate limiting to auth endpoints | Login and register endpoints have no rate limiting, allowing brute-force attacks. Implement rate limiting (e.g., 5 attempts per minute per IP). | src/app/api/auth/register/route.ts, src/lib/auth.ts | M | TODO
2 | Security | CRITICAL | Add CSRF protection to all forms | Contact, estimate, message, and listing forms lack CSRF tokens. Attackers can submit forged requests on behalf of authenticated users. | All API POST routes | M | TODO
3 | Security | CRITICAL | Validate file upload MIME types server-side | Upload route only checks file.type (client-provided), which can be spoofed. Add magic-byte validation using a library like file-type. | src/app/api/upload/route.ts | S | TODO
4 | Security | CRITICAL | Remove pw.txt from project root | A plaintext password file exists in the repository root. Remove immediately, rotate the credentials, and add to .gitignore. | pw.txt, .gitignore | XS | TODO
5 | Security | CRITICAL | Add account lockout after failed login attempts | No lockout mechanism exists. After 5 failed attempts, temporarily lock the account (15-30 min) or require CAPTCHA. | src/lib/auth.ts | M | TODO
6 | Security | CRITICAL | Sanitize all user inputs against XSS | Property descriptions, messages, contact form content, and user names are not sanitized. Use DOMPurify or similar before rendering. | All forms and API routes | M | TODO
7 | Security | CRITICAL | Add rate limiting to translate API | The /api/translate endpoint calls an external API with no rate limiting. This can be abused to generate excessive external API calls. | src/app/api/translate/route.ts | S | TODO
8 | Security | HIGH | Implement Content Security Policy (CSP) headers | No CSP headers are set. Add strict CSP to prevent XSS, clickjacking, and data injection attacks via next.config.ts or middleware. | next.config.ts, src/middleware.ts | M | TODO
9 | Security | HIGH | Add input length validation to all API endpoints | Several endpoints lack max-length checks on string inputs. Property titles, descriptions, and other text fields should have explicit limits. | All API routes | M | TODO
10 | Security | HIGH | Sanitize file paths in upload route | User ID is directly used in file paths without sanitization. Path traversal could potentially be exploited. | src/app/api/upload/route.ts | S | TODO
11 | Security | HIGH | Add email verification flow | Users can register with any email without verification. Implement email confirmation with a time-limited token using Resend (already in deps). | src/app/api/auth/register/route.ts, new verify route | L | TODO
12 | Security | HIGH | Implement password reset flow | No forgot-password functionality exists. Add reset-password via email link with time-limited tokens. | New API routes + pages | L | TODO
13 | Security | MEDIUM | Add Prisma query input validation with Zod | API routes use raw request body values in Prisma queries. Validate all inputs with Zod schemas before database operations. | All API routes | L | TODO
14 | Security | MEDIUM | Hide detailed error messages in production | Some API routes expose error details. Return generic messages in production, log details server-side only. | All API routes | S | TODO
SEO
15 | SEO | CRITICAL | Convert key pages from client to server components | Homepage, properties listing, and property detail are fully client-rendered ('use client'), killing SEO for a property site. Convert to RSC with client islands. | src/app/(main)/page.tsx, properties/page.tsx, [slug]/page.tsx | XL | TODO
16 | SEO | HIGH | Add dynamic metadata to all pages | Most pages lack proper <title> and <meta> tags. Add generateMetadata() to property pages, about, contact, etc. | All page.tsx files | M | TODO
17 | SEO | HIGH | Add JSON-LD structured data for properties | No structured data markup. Add RealEstateListing schema.org markup to property detail pages for rich search results. | src/app/(main)/properties/[slug]/page.tsx | M | TODO
18 | SEO | HIGH | Make html lang attribute dynamic based on locale | html lang='en' is hardcoded. Should reflect the user's selected language (en/fr/de) for accessibility and SEO. | src/app/layout.tsx, src/lib/i18n/context.tsx | S | TODO
19 | SEO | HIGH | Add sitemap.xml and robots.txt | No sitemap or robots.txt exists. Generate dynamic sitemap from published properties for search engine crawling. | New: src/app/sitemap.ts, src/app/robots.ts | M | TODO
20 | SEO | MEDIUM | Add Open Graph and Twitter card meta tags | No social sharing metadata. Add OG image, title, description for property pages to improve link previews on social media. | Property detail page, layout files | M | TODO
21 | SEO | MEDIUM | Implement canonical URLs | No canonical URLs set. Properties accessible via different filter URLs could cause duplicate content issues. | All page layouts | S | TODO
PERFORMANCE
22 | Performance | HIGH | Optimize image loading with Next.js Image | Homepage hero and category images use background-image CSS instead of Next/Image. Lose lazy loading, responsive sizing, and WebP optimization. | src/app/(main)/page.tsx, properties pages | L | TODO
23 | Performance | HIGH | Implement ISR for property pages | Property detail pages are fully client-rendered. Use Incremental Static Regeneration for fast loads + fresh data. | src/app/(main)/properties/[slug]/page.tsx | L | TODO
24 | Performance | MEDIUM | Add loading.tsx and error.tsx boundaries | No loading or error boundaries exist. Add them for proper Suspense fallbacks and error recovery in all route groups. | src/app/(main)/loading.tsx, error.tsx + admin + dashboard | M | TODO
25 | Performance | MEDIUM | Reduce Framer Motion bundle | About page imports full framer-motion instead of LazyMotion. Inconsistent usage across pages increases bundle size. | src/app/(main)/about/page.tsx, contact/page.tsx | S | TODO
26 | Performance | MEDIUM | Add database indexes for common queries | Properties are filtered by city+listingType+status (indexed), but also by bedrooms, livingArea, and price combos which may need composite indexes. | prisma/schema.prisma | S | TODO
27 | Performance | LOW | Implement pagination with cursor-based approach | Current offset pagination (skip/take) is inefficient for large datasets. Cursor-based pagination scales better. | src/app/api/properties/route.ts | M | TODO
UX/UI
28 | UX/UI | HIGH | Add 404 and 500 error pages | No custom error pages exist. Users see generic Next.js errors. Create branded not-found.tsx and error.tsx pages. | New: src/app/not-found.tsx, src/app/error.tsx | M | TODO
29 | UX/UI | HIGH | Make property contact form actually submit | The contact form on property detail page has no onSubmit handler - the Send button does nothing. | src/app/(main)/properties/[slug]/page.tsx | S | TODO
30 | UX/UI | HIGH | Add toast/notification system | Success/error feedback is inconsistent. Property detail has a custom toast; other forms show inline errors or nothing. Implement unified toast system. | Components + all form pages | M | TODO
31 | UX/UI | HIGH | Add form validation feedback | Contact, estimate, and registration forms show minimal validation errors. Add inline field-level validation with clear error messages. | All form pages | M | TODO
32 | UX/UI | MEDIUM | Add loading states to all buttons | Submit buttons don't show loading spinners during API calls. Users may double-click causing duplicate submissions. | All forms (contact, estimate, register, login) | S | TODO
33 | UX/UI | MEDIUM | Add empty states for dashboard sections | No listings, no messages, no saved properties all need friendly empty states with CTAs instead of blank screens. | Dashboard pages | S | TODO
34 | UX/UI | MEDIUM | Improve mobile property gallery experience | Mobile users see only the main image with a small 'View all' link. Add swipe-to-browse gesture support. | src/app/(main)/properties/[slug]/page.tsx | M | TODO
35 | UX/UI | MEDIUM | Add property comparison feature | Users can't compare properties side-by-side. Allow selecting 2-3 properties and viewing their details in a comparison table. | New component + page | L | TODO
36 | UX/UI | LOW | Add skeleton loading for property cards | While property cards already have basic skeleton loading, make them more realistic with proper card shapes and shimmer effects. | Properties listing page | S | TODO
37 | UX/UI | LOW | Add back-to-top button | Long property listing pages have no quick way to scroll back up. Add a floating back-to-top button. | Main layout or new component | XS | TODO
ACCESSIBILITY
38 | Accessibility | HIGH | Add ARIA labels to all interactive elements | Language switcher, user menu, mobile menu, gallery controls, and filter buttons lack proper ARIA attributes (aria-label, aria-expanded, etc.). | header.tsx, property detail, properties list | M | TODO
39 | Accessibility | HIGH | Add keyboard navigation to dropdowns and modals | Language dropdown, user menu, gallery modal, and filter dropdowns can't be navigated with keyboard (Tab, Enter, Escape, Arrow keys). | header.tsx, property detail gallery | M | TODO
40 | Accessibility | MEDIUM | Add focus management for modals and overlays | Gallery modal and contact form expansion don't trap focus. Screen reader users can tab behind the modal. | Property detail page | M | TODO
41 | Accessibility | MEDIUM | Add alt text to all images | Property images in listing cards use background-image divs with no alt text. Switch to Next/Image with descriptive alt. | Homepage, properties listing | M | TODO
42 | Accessibility | MEDIUM | Add skip-to-content link | No skip navigation link for keyboard/screen reader users to bypass the header navigation. | src/app/(main)/layout.tsx | XS | TODO
43 | Accessibility | LOW | Ensure color contrast meets WCAG AA | Some text colors (white/50 = 50% opacity white, #6B6B6B on white) may not meet 4.5:1 contrast ratio. Audit and fix. | All pages | M | TODO
CODE QUALITY
44 | Code Quality | HIGH | Remove 'as any' TypeScript casts | Register route uses 'prisma.user.create as any'. Fix Prisma types properly instead of casting to any. | src/app/api/auth/register/route.ts | S | TODO
45 | Code Quality | HIGH | Centralize API response handling | Each API route has its own try/catch with inconsistent error formats. Create shared error handler and response helper. | All API routes | M | TODO
46 | Code Quality | HIGH | Extract reusable components | Property cards, loading skeletons, and Reveal animations are duplicated across pages. Create shared components. | Homepage, properties, about, contact | M | TODO
47 | Code Quality | MEDIUM | Create shared Zod validation schemas | Email regex, password rules, and field length validations are repeated in multiple routes. Centralize into shared schemas. | src/lib/validations.ts (new) | M | TODO
48 | Code Quality | MEDIUM | Consistent Prisma import style | Some files import { prisma } from '@/lib/prisma', others use default import. Standardize across all files. | src/app/api/user/messages/route.ts and others | S | TODO
49 | Code Quality | MEDIUM | Add API route tests | No test files exist in the project. Add at least integration tests for critical API routes (auth, properties, upload). | New: __tests__/ directory | XL | TODO
50 | Code Quality | LOW | Add TypeScript strict mode checks | Enable stricter TS options (noUncheckedIndexedAccess, strictNullChecks fully enforced) to catch potential runtime errors. | tsconfig.json | M | TODO
51 | Code Quality | LOW | Add pre-commit hooks (lint + type-check) | No git hooks configured. Add husky + lint-staged for automatic linting and type checking before commits. | package.json, new .husky/ config | S | TODO
I18N
52 | i18n | HIGH | Complete French and German translations | Translation files may have missing keys. Audit all three dictionaries (en.json, fr.json, de.json) for completeness and consistency. | src/lib/i18n/dictionaries/*.json | L | TODO
53 | i18n | HIGH | Add URL-based locale routing | Language is stored client-side only. Implement /en/, /fr/, /de/ URL prefixes for SEO and shareable localized links. | src/middleware.ts, all routes | XL | TODO
54 | i18n | MEDIUM | Translate property features and types in UI | Property type names (APARTMENT, HOUSE) and features show as raw enum values. Map to translated display names. | Properties pages, i18n dictionaries | M | TODO
55 | i18n | MEDIUM | Add locale-aware number and date formatting | Prices use comma formatNumber() everywhere. Use Intl.NumberFormat with locale for proper EUR formatting (1.000.000 vs 1,000,000). | Homepage, properties pages | M | TODO
56 | i18n | LOW | Persist locale preference to user account | Language selection is stored in localStorage. For logged-in users, save preference to their profile for cross-device consistency. | src/lib/i18n/context.tsx, user API | S | TODO
NEW FEATURE
57 | New Feature | IDEA | Add property map view with Mapbox/Leaflet | Properties listing only has a grid view. Add a split-view with an interactive map showing property pins. Click pin to see card. | New: src/components/property-map.tsx | XL | TODO
58 | New Feature | IDEA | Add virtual tour / 360 photo support | Allow property owners to upload 360-degree photos or link to Matterport tours. Display in an immersive viewer on detail page. | Property model, upload route, detail page | XL | TODO
59 | New Feature | IDEA | Implement saved search alerts | SavedSearch model exists but has no alert implementation. Send email notifications when new properties match saved criteria. | New cron job / API route, email templates | L | TODO
60 | New Feature | IDEA | Add property price history / market trends | Track price changes over time and show chart on property detail. Display neighborhood average price trends. | New model PriceHistory, chart component | XL | TODO
61 | New Feature | IDEA | Add agency public profile pages | Agency model exists but there's no /agencies page or /agencies/[slug] detail. Show agency listings, team, reviews. | New: src/app/(main)/agencies/ pages | L | TODO
62 | New Feature | IDEA | Add live chat or WhatsApp integration | Contact forms are async. Add real-time chat option or WhatsApp click-to-chat for immediate inquiries about properties. | New component, property detail page | M | TODO
63 | New Feature | IDEA | Add property video walkthroughs | Support video uploads or YouTube/Vimeo embeds for property walkthroughs alongside the photo gallery. | Upload route, property model, detail page | L | TODO
64 | New Feature | IDEA | Add neighborhood guide / area information | Show nearby amenities (schools, transport, shops), walkability score, and area demographics on property detail pages. | New component, possibly external API integration | XL | TODO
65 | New Feature | IDEA | Add document management for listings | PropertyDocument model exists but no UI to upload/view floor plans, energy certificates, or legal documents. | Dashboard listing form, property detail page | L | TODO
66 | New Feature | IDEA | Add user reviews / testimonials system | Allow verified buyers/renters to leave reviews for agents and agencies. Display on about page and agent profiles. | New Review model, components, pages | L | TODO
67 | New Feature | IDEA | Implement Google/Apple OAuth sign-in | Only credentials auth is active. Add Google and Apple OAuth providers for faster sign-up and better conversion. | src/lib/auth.ts, login page | M | TODO
68 | New Feature | IDEA | Add property analytics dashboard for owners | Show property owners how many views, inquiries, favorites, and search appearances their listings get over time. | Dashboard page, new analytics API | L | TODO
69 | New Feature | IDEA | Add dark mode support | Site only has a light theme. Add dark mode toggle using CSS variables and system preference detection. | globals.css, all components, header toggle | L | TODO
70 | New Feature | IDEA | Add advanced mortgage calculator with amortization | Current calculator shows monthly payment only. Add full amortization table, chart, and comparison between banks. | Homepage mortgage section or dedicated page | M | TODO
71 | New Feature | IDEA | Add property PDF brochure generation | Let users download a professional PDF brochure of a property with photos, details, floor plan, and agent contact info. | New API route with PDF generation | L | TODO
72 | New Feature | IDEA | Implement push notifications (PWA) | Add service worker and push notifications for new messages, listing status changes, and saved search matches. | New: service-worker.ts, notification API | XL | TODO
73 | New Feature | IDEA | Add multi-currency support (EUR/USD/GBP) | International buyers may prefer prices in their currency. Add currency converter toggle using live exchange rates. | New component, currency API, all price displays | M | TODO
INFRASTRUCTURE
74 | Infrastructure | HIGH | Set up proper environment variable management | Supabase vars are referenced but NEXT_PUBLIC_SUPABASE_URL is inconsistently used. Ensure all env vars are documented and validated at startup. | .env, next.config.ts | S | TODO
75 | Infrastructure | HIGH | Add proper logging system | Only console.error/log is used. Implement structured logging (e.g., Pino) for production error tracking and debugging. | All API routes | M | TODO
76 | Infrastructure | MEDIUM | Set up CI/CD pipeline | No CI/CD configuration exists. Add GitHub Actions for linting, type-checking, building, and deploying on push/PR. | New: .github/workflows/ | M | TODO
77 | Infrastructure | MEDIUM | Add database seed script | No seed data for development. Create a Prisma seed script with sample properties, users, and agencies for local dev. | New: prisma/seed.ts | M | TODO
78 | Infrastructure | MEDIUM | Configure proper CORS headers | No explicit CORS configuration. Add appropriate headers for API routes, especially for the translate and upload endpoints. | next.config.ts or middleware | S | TODO
79 | Infrastructure | LOW | Add health check endpoint | No /api/health endpoint for monitoring. Add one that checks database connectivity and returns service status. | New: src/app/api/health/route.ts | XS | TODO
LEGAL
80 | Legal | HIGH | Complete legal page content | Privacy policy, terms, cookie policy, and imprint pages likely need real legal content specific to Luxembourg law (GDPR, consumer protection). | src/app/(main)/legal/* pages | L | TODO
81 | Legal | HIGH | Implement proper cookie consent management | Cookie banner exists but may not properly block analytics/marketing cookies before consent. Verify GDPR compliance. | src/components/cookie-consent.tsx | M | TODO
82 | Legal | MEDIUM | Add data export / deletion (GDPR Article 15 & 17) | Users have no way to export their data or request account deletion. Required under GDPR for EU users. | New: dashboard settings, API routes | L | TODO
83 | Legal | MEDIUM | Add terms acceptance during registration | Registration form doesn't require explicit acceptance of terms and privacy policy. Add mandatory checkbox. | src/app/(auth)/register/page.tsx | S | TODO

## Summary
XACT.LU PROJECT AUDIT SUMMARY
BY PRIORITY
Priority | Count | % of Total
CRITICAL | 8 | 10%
HIGH | 26 | 31%
MEDIUM | 24 | 29%
LOW | 8 | 10%
IDEA | 17 | 20%
TOTAL | 83 | 100%
BY CATEGORY
Category | Count | Critical | High
Security | 14 | 7 | 5
SEO | 7 | 1 | 4
Performance | 6 | 0 | 2
UX/UI | 10 | 0 | 4
Accessibility | 6 | 0 | 2
Code Quality | 8 | 0 | 3
i18n | 5 | 0 | 2
New Feature | 17 | 0 | 0
Infrastructure | 6 | 0 | 2
Legal | 4 | 0 | 2
EFFORT LEGEND
XS | < 1 hour
S | 1-4 hours
M | 4-8 hours (1 day)
L | 2-5 days
XL | 1-2 weeks
STATUS OPTIONS
TODO
IN PROGRESS
DONE
SKIPPED